# Clinara Integration Playbook (version 2, approved by the ELT, May 2024)

Fictional demonstration document.

# Integration philosophy

We buy specialist clinic software and integrate it onto the Clinara platform: one product, one CRM, one billing engine.

Customers come first: no customer should experience disruption in the first 100 days.

Acquired brands are retired within 12 months unless the Board agrees a standalone or partial integration.

We integrate fully by default; partial integration (keep brand and product, integrate finance and sales) applies to capability acquisitions.

# Acquisition types

Full integration: specialist software with overlapping customers; migrate onto the Clinara platform within 12 months.

Partial integration: capability acquisition where the product and brand stay separate; integrate finance, people and go-to-market.

# Workstream: Strategy and governance

Pre-completion: appoint integration leader and sponsor (Owner: CEO). Completion criteria: named leader with at least 50% of their time allocated.

Day 1: hold integration steering committee kick-off (Owner: Integration leader). Milestone.

First 30 days: agree target operating model and decision rights (Owner: CEO). Approval: CEO. Completion criteria: TOM signed off by the ELT.

Weekly: integration status report to the ELT (Owner: Integration leader).

# Workstream: Finance

Day 1: take control of bank accounts and payment authorities (Owner: CFO). Critical path. Completion criteria: dual signatories from Clinara on every account.

First 30 days: align month-end reporting to the Clinara calendar (Owner: CFO). Completion criteria: first month-end closed within 5 working days.

First 100 days: migrate billing onto Clinara Pay (Owner: CFO). Depends on: CRM migration. Completion criteria: 100% of invoices issued from Clinara Pay.

# Workstream: Commercial

Day 1: customer announcement email from both CEOs (Owner: CCO). Approval: CEO.

First 30 days: assign account owners for every acquired customer (Owner: CCO). Completion criteria: every active customer has a named Clinara account owner in the CRM.

Day 60: migrate customer records into the Clinara CRM (Owner: Head of RevOps). Critical path. Completion criteria: all active accounts, contacts and open opportunities migrated and reconciled.

First 100 days: launch cross-selling of Clinara modules to acquired customers (Owner: CCO). Depends on: CRM migration. Completion criteria: cross-sell pipeline reported weekly.

# Workstream: People

Pre-completion: identify key employees and agree retention arrangements (Owner: People Director). Approval: CEO.

Day 1: all-hands announcement to acquired employees (Owner: CEO).

First 30 days: payroll and benefits mapped onto Clinara providers (Owner: People Director). Completion criteria: first payroll run without errors.

# Workstream: Technology

Pre-completion: systems inventory of the target (Owner: CTO).

First 30 days: single sign-on and identity onto Clinara Entra ID (Owner: CTO). Completion criteria: all acquired staff on Clinara identity with MFA enforced.

First 100 days: product migration plan agreed (Owner: CPTO). Approval: CEO.

# Workstream: Legal and compliance

Pre-completion: change-of-control consents from key customers and suppliers (Owner: General Counsel). Critical path.

First 30 days: insurance policies extended to the acquired company (Owner: CFO).

First 30 days: data protection review and ICO registration updated (Owner: General Counsel).

# Risks and escalation

Risk: customer churn after announcement. Escalate to the CEO if more than 2% of ARR gives notice in the first 100 days.

Risk: loss of key engineers. Escalate to the CEO on any resignation of a key employee.

Risk: CRM migration slips and delays cross-selling. Escalate to the steering committee if the migration is more than two weeks late.

# Integration KPIs

Gross revenue retention of acquired customers (target at least 95%).

Cross-sell ARR from acquired customers.

Integration milestones achieved on time (target at least 80%).

# Synergy tracking

Synergies are tracked monthly by the CFO against the investment case.

Only invoiced revenue and booked savings count as realised; forecasts are reported separately.