## DentalDesk plan
Workstream | Activity | Owner | Timing | Planned | Actual | Status | Notes
Strategy and governance | Appoint integration leader | CEO | Pre-completion | 2023-02-20 | 2023-02-20 | Done
Finance | Bank accounts and payment authorities | CFO | Day 1 | 2023-03-01 | 2023-03-01 | Done
Commercial | Customer announcement email | CCO | Day 1 | 2023-03-01 | 2023-03-01 | Done
Commercial | Customer data cleansing | Head of RevOps | First 30 days | 2023-03-31 | 2023-05-12 | Done late | Duplicate practice records and missing contacts; took six weeks longer than planned
Commercial | Migrate customer records into the Clinara CRM | Head of RevOps | Day 60 | 2023-04-30 | 2023-06-16 | Done late | Blocked by data cleansing
Commercial | Launch cross-selling to acquired customers | CCO | First 100 days | 2023-06-09 | 2023-08-01 | Done late | Started after CRM migration
People | Payroll and benefits mapped | People Director | First 30 days | 2023-03-31 | 2023-03-28 | Done
Technology | Single sign-on onto Clinara identity | CTO | First 30 days | 2023-03-31 | 2023-04-14 | Done
Legal and compliance | Change-of-control consents | General Counsel | Pre-completion | 2023-02-27 | 2023-02-27 | Done
Brand and communications | Retire DentalDesk brand | CMO | Month 12 | 2024-03-01 | 2024-02-15 | Done