## Slide 1: OptiBook 100-day integration plan (fictional)
Completion 1 July 2024
Full integration onto the Clinara platform
Integration leader: Head of Integration

## Slide 2: Commercial workstream
Day 1: customer announcement email (Owner: CCO)
First 30 days: customer data cleansing (Owner: Head of RevOps)
Day 60: migrate customer records into the Clinara CRM (Owner: Head of RevOps). Critical path
First 100 days: launch cross-selling to acquired customers (Owner: CCO). Depends on: CRM migration

## Slide 3: Technology workstream
Pre-completion: systems inventory (Owner: CTO)
First 30 days: single sign-on onto Clinara identity (Owner: CTO)
First 100 days: product migration plan agreed (Owner: CPTO)

## Slide 4: Finance workstream
Day 1: bank accounts and payment authorities (Owner: CFO)
First 100 days: migrate billing onto Clinara Pay (Owner: CFO). Depends on: CRM migration

## Slide 5: Status at day 100
CRM migration completed on day 94, 34 days late: data quality issues were found only after completion
Cross-selling launched on day 120, missing the 100-day milestone
Billing migration slipped to day 130